## Sheet1
Task No. | Tasks Description | Owners | Start Date (mm/dd/yyyy) | End Date (mm/dd/yyyy) | Duration (hours) | % Completion | Status
Migration Phase (SQL Server to PostgreSQL Northwind Database Migration)
1 | Configure Northwind DB on SQL Server | DBA | 2024-06-15 | 2024-06-15 | 10 min | 100% | Close Complete
2 | Congifure Replication on SQL Server and configure subsciber and publisher as well. | DBA | 2024-06-15 | 2024-06-15 | 20 min | 100% | Close Complete
3 | Configure CDC for capture changes performed to continues replication using DMS | DBA | 2024-06-15 | 2024-06-15 | 20 min | 100% | Close Complete
4 | Create S3 storage on AWS Portal | DBA | 2024-06-15 | 2024-06-15 | 20 min | 100% | Close Complete
5 | Configure IAM role for S3 storage | DBA | 2024-06-15 | 2024-06-15 | 5 min | 100% | Close Complete
6 | Configure AWS PostgreSQL RDS instance | DBA | 2024-06-15 | 2024-06-15 | 30 min | 100% | Close Complete
7 | Configure Inbound and Outbound rules | DBA | 2024-06-15 | 2024-06-15 | 10 min | 100% | Close Complete
8 | Create AWS Data Migration replication instance with ongoing replication Configure endpoints like source as SQL Server IP and port number and Destination as PostgreSQL IP and Port number and repective logins | DBA | 2024-06-15 | 2024-06-15 | 30 min | 100% | Close Complete
9 | Download SCT and install on local maschine | DBA | 2024-06-15 | 2024-06-15 | 10 min | 100% | Close Complete
10 | Create new project on SCT and create AWS Profile using Access key and Secret key | DBA | 2024-06-15 | 2024-06-15 | 10 min | 100% | Close Complete
11 | Download and Install MSSQL and PostgreSQL JDBC Drivers | DBA | 2024-06-15 | 2024-06-15 | 10 min | 100% | Close Complete
12 | Select Soruce and Target database and objects to be migrated | DBA | 2024-06-15 | 2024-06-15 | 10 min | 100% | Close Complete
13 | Run the SCT task using load schema option | DBA | 2024-06-15 | 2024-06-15 | 5 min | 100% | Close Complete
14 | Click on aply to the database on target PostgreSQL to create the converted objects | DBA | 2024-06-15 | 2024-06-15 | 5 min | 100% | Close Complete
15 | Some objects are not able to convert which need maual efforts to convert same.
16 | Create a Data Migration Task use the Replication instance created to run the task. Use the end points as source and target repectively. Choose the migration type as migrate existing data or migrate existing data and replicate ongoing changes or just replicate data changes only | DBA | 2024-06-15 | 2024-06-15 | 30 min | 100% | Close Complete
17 | Validate the Data migration task status until db is 100% replicated. | DBA | 2024-06-15 | 2024-06-15 | 30 min | 100% | Close Complete
18 | Once all data is replicated we can point the application to PostgreSQL Database and test it. | App Team | 2024-06-15 | 2024-06-15 | 30 min
19 | Perform application cutover | App Team | 2024-06-15 | 2024-06-15 | 30 min
20 | Sign off from respective teams
Database Migration Completed Successfully.